## general_report
External issue ID | Key | Component/s | Summary | Description | Expected Behaviour | Actual Behaviour | Impacted Products | Status | Fix Version/s | Affects Version/s | Issue Type
| ARDAAAF-496 | General | Duplicate and missing entries in BSWMDT file | Duplicate and missing entries in BSWMDT file | NA | NA | N/A | Acceptance | Ver4.02.00.D | E4.40, Ver4.00.00, Ver4.01.00 | Bug
| ARDAAAF-2067 | SPI | Naming convention wrong for 'usReserved1', member of structure Spi_CsihOsRegs | In Spi_LTType.h, inside Spi_CsihOsRegs, member usReserved1 is uint 32 type. Hence the member shall be renamed as ulReserved1 | member usReserved1 is uint 32 type. Hence the member shall be renamed as ulReserved1 | Naming convention wrong for 'usReserved1', member of structure Spi_CsihOsRegs | Code | Open |  | Ver4.01.00.001 | Bug
| ARDAAAF-1877 | General | Wrong User mode and Supervisor mode information in Usermanual | As per RH850/P1x-C Group user manual(6.4 Interrupt Controller Control Registers),Writing to the EICn and IMRm registers is enabled only in supervisor mode (PSW.UM = 0)and so if any of these registers are used by Driver API's for writing it should be accessed only in supervisor mode .Other API can be accessed in both User mode and Supervisory mode. This information is not correctly updated in "User Mode and Supervisor Mode" section of EUM . Modules affected : FLS,SPI,ADC (Check the names of the API's Adc_EnableHwTrigger() and Adc_DisableHwTrigger),MCU,LIN and FR(No such table exist),ICU,PWM Note: Description is edited as the issue was initially reported for FLS module only. | User mode and supervisor mode table in usermanual shall describe the APIs which can be run in user mode and supervisory mode. | "User Mode and Supervisor Mode" section of EUM is not updated correctly | Document | Design | Ver4.02.01.D | Ver4.01.00.001 | Bug
| ARDAAAF-1641 | SPI | Description about hardware errors in SPI communication are not present in CUM | Generally, following types of errors can be detected for SPI communication : Data consistency error (transmission data) Parity error (received data) Overrun error 1.There is no description for these errors in CUM. 2.Description of DEM error 'SPI_E_HARDWARE_ERROR' mention only about 'overrun error'.Other two hardware errors are not mentioned . | Description about all hardware errors and the information ,'how these errors are handled in MCAL', needs to be present in CUM | Description about hardware errors in SPI communication are not present in CUM | Document | Design | Ver4.02.01.D | Ver4.01.00 | Bug
| ARDAAAF-1833 | MCU | Callback notifications should be generated on Mcu_Cbk.h files | All callback notifications from maskable and non-maskable interrupts should be generated on Mcu_Cbk.h. Currently it is generated on Mcu_Cfg.h. Changes has to be made on tool code to move the call back functions from Mcu_Cfg.h to Mcu_Cbk.h file. | See description | See description | Generator | Design | Ver4.02.01.D | Ver4.01.00 | Bug
| ARDAAAF-1994 | SPI | UUIDs are not unique in BSWMDT file | In BSWMDT file, UUIDs for certain elements are not unique. If we are running AMDC tool with BSWMDT file, a warning with Rule A220 will be thrown: Example:(FLS) Rule A220: UUID 'ECUS:9b933fde-9d34-4dd0-863b-3c6c057abcfc' is not unique for 'BswCalledEntity_1' | All UUIDs should be unique | All UUIDs are not unique | PDF | Design | Ver4.02.01.D | Ver4.01.00.001 | Bug
| ARDAAAF-1404 | FLS | Non effective condition in the IF check in Fls.c | In Fls.c, the conditions C1: ((TargetAddress - (uint32)FLS_DF_SECTOR_START_ADDRESS) > ((uint32)FLS_DF_TOTAL_SIZE - (uint32)FLS_ONE)) and the condition C2: (((TargetAddress - (uint32)FLS_DF_SECTOR_START_ADDRESS) + Length) >(uint32)FLS_DF_TOTAL_SIZE) in Fls_Write API are not covered in UT. Also Functional test cases shall be improved for DET checks. | NA | NA | Code, Document | Design | Ver4.02.01.D | Ver4.01.00 | Bug
| ARDAAAF-1874 | PWM | The result of multiplication can cause overflow, when (same variable type) two 32bit variables multiplied | [PWM] In Pwm_HW_CalculateDuty() Api Two 32bit variables are multiplied,So this expression is done 32bit calculation. For example : At line 1181 of Pwm_LLDriver.c calculates bellow: LddAbsoluteDuty = ((LddAbsolutePeriod * LddRelativeDuty) >> PWM_DUTY_CALC_DIV); Here LddAbsolutePeriod and LddRelativeDuty are 32bits. The maximum number of LddAbsolutePeriod may be 4294967295 when TAUJ is used for PWM. The maximum number of LddRelativeDuty may be 0x8000; So this operation is done 32bit calculation and the result of this multiplication can be overflowed. | ((LddAbsolutePeriod * LddRelativeDuty) >> PWM_DUTY_CALC_DIV); Here LddAbsolutePeriod and LddRelativeDuty are 32bits and the result of this multiplication can be overflowed. To avoid to overflow, at least, one of the lefter or righter expression of ‘*’ operator should be 64bit. | ((LddAbsolutePeriod * LddRelativeDuty) >> PWM_DUTY_CALC_DIV); Here LddAbsolutePeriod and LddRelativeDuty are 32bits and the result of this multiplication can be overflowed. | Code | Design | Ver4.02.01.D | Ver4.01.00, Ver4.01.00.001 | Bug
| ARDAAAF-2000 | SPI | Variable Spi_GblQueueStatus is not updated as SPI_QUEUE_FILLED when jobs are queued | Global variable 'Spi_GblQueueStatus' is used to store the status of job queue Spi_GaaJobQueue . Before the queue is filled, status needs to be changed to SPI_QUEUE_FILLED. If queue is empty status should be SPI_QUEUE_EMPTY. But as per current implementation status of queue is not updated as SPI_QUEUE_FILLED after following line inside Spi_scheduler.c , inside function Spi_PushRemainingJobsToQueue: {code:java} if (SPI_QUEUE_EMPTY == Spi_GblQueueStatus[LucQueueIndex]) { ---------------------------- } {code} | Global variable 'Spi_GblQueueStatus' should be updated correctly | Variable Spi_GblQueueStatus is not updated as SPI_QUEUE_FILLED when jobs are queued | Code | Design | Ver4.02.01.D | Ver4.01.00.001 | Bug
28702 | ARDAAAF-1393 | FLS | AUTOSAR deviation regarding time-out monitoring is missing from user documentation | Problem description: Time-out monitoring is not implemented for Erase/Write operations. This is because Erase/Write commands are performed in interrupt mode also but all other commands are performed in polling mode only. But this is a violation of following AUTOSAR requirements. <i>FLS272: If development error detection for the module Fls is enabled: the function Fls_MainFunction shall provide a timeout monitoring for the currently running job, that is it shall supervise the deadline of the read / compare / erase or write job. FLS359: If development error detection for the module Fls is enabled: the function Fls_MainFunction shall check, whether the configured maximum erase time (see FLS298_Conf FlsEraseTime) has been exceeded. If this is the case, the function Fls_MainFunction shall raise the development error FLS_E_TIMEOUT. FLS360: If development error detection for the module Fls is enabled: the function Fls_MainFunction shall check, whether the expected maximum write time (see note below) has been exceeded. If this is the case, the function Fls_MainFunction shall raise the development error FLS_E_TIMEOUT.</i> But these violations are not documented properly in Usermanuals. | All autosar deviations shall be properly documented in UM to inform user. | Deviation of FLS272,FLS359 and FLS360 are not mentioned in UM. | Document | Design | Ver4.02.01.D | Ver4.01.00 | Bug
| ARDAAAF-1826 | SPI | CSIHn Status Register is not cleared after data consistency error,which blocks SPI transmission using Spi_synchtransmit function | When Spi_Synchtransmit is called transmission is blocked under following conditions: 1.When data consistency error occurs CSIHnSRT0.DCE bit is set. and corresponding sequence is failed. 2.Then if same sequence or another sequence using same hardware unit is called , then those sequences also report data consistency error even if the error is not triggered, because CSIHn Status Register is not cleared after data consistency error. | CSIHn Status Register should be cleared after data consistency error | CSIHn Status Register is not cleared after data consistency error,which blocks SPI transmission using Spi_synchtransmit function | Code, Test | Design | Ver4.02.01.D | Ver4.01.00.001 | Bug
| ARDAAAF-1637 | General | Violation of Autosar requirement ecuc_sws_1014 is not documented | It has been detected, that Autosar specification ecuc_sws_1014 is violated in our PDF files. For F1x MCAL (except F1K), P1M and P1x-C this should not be corrected. However, this limitation has to be added for these MCAL in the AUTOSAR_Modules_Overview document. | Violation of Autosar requirement ecuc_sws_1014 shall be mentioned in the documentation. | Violation of Autosar requirement ecuc_sws_1014 is not mentioned in the documentation | Document | Design | Ver4.02.01.D | Ver4.01.00 | Bug
| ARDAAAF-2023 | LIN | UUIDs are not unique in BSWMDT file | In BSWMDT file, UUIDs for certain elements are not unique. If we are running AMDC tool with BSWMDT file, a warning with Rule A220 will be thrown: Example:(FLS) Rule A220: UUID 'ECUS:9b933fde-9d34-4dd0-863b-3c6c057abcfc' is not unique for 'BswCalledEntity_1' | To do AMDC check for BSWMDT files for all MCAL modules and make sure that all UUIDs are unique (Rule A220). | All UUIDs should be unique | PDF | Design | Ver4.02.01.D | Ver4.01.00.001 | Bug
| ARDAAAF-2063 | MCU | Polyspace Red Warnings present in E-Code. | There are red Polyspace warnings present in the E-Code. According to the document 'Polyspace Autosar User Guidelines': All red findings will be removed immediately upon detection. Polyspace was run on the Work Products with Revision: 367389 Polyspace reports are at the following repository: https://172.29.44.209/automotive/autosar/svnASG_D008633/dev/bsw/Autosar_R40/branch/dev_mcal_P1x-C_R403-OpenMarket/internal/X1X/P1x-C/modules/mcu/test_static/polyspace/4.0.3 | Polyspace report should not have red warnings. | Polyspace report have red warnings. | Code | Open |  | Ver4.02.00.D | Bug
24045 | ARDAAAF-1310 | General | Please describe the processor name CPU1(PE1) to UM, Release Note, Readme to clarify the conditions of running Mcal. | Please describe the processor name CPU1(PE1) to UM, Release Note, Readme to clarify the conditions and environment of running Mcal. For Instance, <device number> will be changed to <device number>(CPU1(PE1)) in readme.txt, Release Note.txt, Component UM and so on. According to the user manual, the Main CPU is called "CPU1(PE1)". | NA | NA | Document | Acceptance | Ver4.02.00.D | E4.40, Ver4.01.00, Ver4.01.00.001 | Bug
29620 | ARDAAAF-326 | General | Wrong heading for stub files in Component User Manual | Problem description: The heading description provided for stub files in CUM chapter 8 is wrong. The heading description for the stub files should be "The Stub C header files" and the other stub files should also need to be mentioned e.g. Det.h, Rte.h, SchM.h etc. But the stub files are mentioned as "The port specific C header files" which need to be corrected. Expected behavior: The heading should be "The Stub C header files:" and missing stub files should be added. Actual behavior: The heading is "The port specific C header files" and all the stub files are not mentioned. |  |  | Document | Acceptance | Ver4.02.00.D | E4.40, Ver4.00.00, Ver4.01.00 | Bug
18373 | ARDAAAF-460 | General | PortNumberOfPortPins with fix value 0 | PortNumberOfPortPins is defined as Min=0 Max=0 and the description says that this parameter is not used. Our configuration tool validates the parameter according to Autosar standard and, because there is at least one PortPin configured(due to lower multiplicity 1), produces an error message. Therefore, PortNumberOfPortPins should have a reasonable range, although it is not used | PortNumberOfPortPins should have a reasonable range, although it is not used. | The Generation tool validates the parameter according to Autosar standard and, because there is at least one PortPin configured(due to lower multiplicity 1), it produces an error message. | PDF | Acceptance | Ver4.02.00.D | Ver4.00.00, Ver4.01.00 | Bug
| ARDAAAF-2065 | LIN | LIN channel status being changed on wakeup request even before Lin_CheckWakeup is called | LIN channel status being changed on wakeup request even before Lin_CheckWakeup is called. In the event of a wake up request , the channel status is changed from LIN_CH_SLEEP to LIN_OPERATIONAL in Lin_WakeUpFromBus() function ,before the validation of the wake up event in Lin_CheckWakeup () API. As a result , If DET is ON , the DET check in Lin_CheckWakeup (Ref: LIN109) if (LIN_CH_SLEEP != Lin_GpChannelRamData[Channel].ucChannelStatus) { } will always be true , reporting DET every time the function is invoked. Also , the sleep request flag ucSlpRqst_RespRdy is set in Lin_WakeUpFromBus irrespective of wakeup support for the channel. | LIN channel status should not be changed on wakeup request in Lin_WakeUpFromBus() function even before Lin_CheckWakeup is called. | LIN channel status being changed on wakeup request in Lin_WakeUpFromBus() function even before Lin_CheckWakeup is called. | Code | Design | Ver4.02.01.D | Ver4.02.00.D | Bug
| ARDAAAF-1638 | SPI | usHWListIndex value are wrong when two Different HW CSIHx used | Even if SpiSupportConcurrentSyncTransmit is set as true, different SpiDeviceAssignment is set for different Job and each job is assigned for different Sequence,Spi_SyncTransmit which is called lator reports SPI_E_SEQ_IN_PROCESS. Probably it is bug of the generator's output for usHWListIndex. All usHWListIndex are same and numeric value.(Probably maximum number assigned for CSIHx that is used on the configuration setting is outputed. CSIH0: 1, CSIH1: 2, CSIH2: 3, CSIH: 4) Seeing source code, it should be bitwise flags those are assigned for CSIHx. e.g. CSIH0: 1, CSHI1: 1<<1, CSIH2: 1<<2, CSIH3: 1<<3. Spi.c (Spi_SyncTransmit) 3129: /* Check the value of Global variable for Hardware status */ 3130: if (SPI_ZERO == (Spi_GusHwStatus & (LpSeqConfig->usHWListIndex))) ^ & operation may expect flag. 3131: { 3132: #if (SPI_CRITICAL_SECTION_PROTECTION == STD_ON) 3133: /* MISRA Violation: START Msg(2:3138)-13 */ 3134: /* Disable relevant interrupts */ 3135: SPI_ENTER_CRITICAL_SECTION(SPI_RAM_DATA_PROTECTION); 3136: /* END Msg(2:3138)-13 */ 3137: #endif 3138: 3139: /* Updating the status of the hardware */ 3140: Spi_GusHwStatus = (Spi_GusHwStatus ¦ (LpSeqConfig->usHWListIndex)); ^ ¦ operation may expect flag. 3141: 3142: #if (SPI_CRITICAL_SECTION_PROTECTION == STD_ON) 3143: /* MISRA Violation: START Msg(2:3138)-13 */ 3144: /* Enable relevant interrupts */ 3145: SPI_EXIT_CRITICAL_SECTION(SPI_RAM_DATA_PROTECTION); 3146: /* END Msg(2:3138)-13 */ 3147: #endif 3148: } | usHWListIndex value are wrong when two Different HW CSIHx used | usHWListIndex value should be genertaed correctly, when two Different HW CSIHx used | Code, Generator | Analysis |  | Ver4.01.00, Ver4.01.00.001 | Bug
| ARDAAAF-2009 | ADC | Group notification occurs on the Limit check enabled channels even for out of range input | Group Notification occurs with Limit check enabled channel with out of bound values. This violates the Autosar requirements ADC449, ADC448 | No group complete notification with out of bound input values. ADC449, ADC448 | Group notification occures for out of bound input for the limit check enabled channels | Code | Open |  | Ver4.02.00.D | Bug
| ARDAAAF-1607 | ETH | Range of EthRxBufTotal/EthTxBufTotal differs between PDF and Code Generator | As per AUTOSAR, the parameters EthRxBufTotal and EthTxBufTotal can have the range 0 to 255. The same range is allowed in PDF. But code generator will throw error if the above parameters are configured above 16. [ERR_59_88_006] : Range ERROR: Total number of Transmit buffer configured is :17 Range for the Total number of Transmit buffers should be with in 0 to 16 [ERR_59_88_007] : Range ERROR: Total number of Receive buffer configured is :17 Range for the Total number of Receive buffers should be with in 0 to 16 | Range of parameters in PDF shall be allowable range and CG shall not report any error for this range. | CG is throwing error if EthRxBufTotal of EthTxBufTotal is configured above 16. | Generator | Acceptance | Ver4.02.00.D | Ver4.01.00 | Bug
| ARDAAAF-1584 | ETH | MAC Address cannot be configured other than that of Renesas | In the current ETH driver, the parameter 'EthMacAddress' can used to configure the MAC address. If EthMacAddress in /AUTOSAR/EcucDefs_Eth/Eth0/EthConfigSet0/EthCtrlConfig0 is set to a different value other than 74:90:50:xx:xx:xx , then generator throws: {code:java} [CG_ERROR] - [ERR_59_88_005] Non Renesas MAC Address configured 75.90.50.00.00.00 . MAC Address shou ld start with 74:90:50:... [CG_ERROR] - Code Generation Failed [CG_ERROR] - Execution Stopped {code} The first 3 bytes of MAC address(EthCtrlPhyAddress) are called Organizationally Unique Identifier (OUI) externally assigned, the next 3 bytes are called Network Interface Controller Specific (NIC) locally administered. Each manufacturer has its own OUI and this is intended to identify the manufacturer not chip vendor. | Customer shall be able to use their OUI in the MAC address | ETH CG throws error if the MAC address contains OUI other than that of Renesas | Generator | Acceptance | Ver4.02.00.D | Ver4.01.00 | Bug
| ARDAAAF-1996 | MCU | Validation for the prohibited bit setting of PLL0FREQ bits for P1H-C device has not been taken care. | The PLL0FREQ(Bit positions 31 and 30 respectively) bits supports values '00', '01', '10'. *P1M-C, P1H-CE* 00: PLL0 = 480MHz and CLK_CPU = 120MHz 01: PLL0 = 320MHz and CLK_CPU = 160MHz 10: PLL0 = 480MHz and CLK_CPU = 240MHz 11: prohibited setting However as per the description given for 'OPBT1 — Option Byte 1' in the Hardware user Manual, the P1H-C device does not support setting of '00' into these bits. *P1H-C* 00: prohibited setting 01: PLL0 = 320MHz and CLK_CPU = 160MHz 10: PLL0 = 480MHz and CLK_CPU = 240MHz 11: prohibited setting Validation of this has to be taken care by the tool code. Parameter 'McuOPBT1Sel' inside container 'McuPLLClkSetting' can be used to validate the same. | Validation of prohibited setting of PLL0FREQ bits in the OPBT1 for P1H-C device has to be taken care of. | Validation of prohibited setting of PLL0FREQ bits in the OPBT1 for P1H-C device has not been taken care of. | Generator | Open |  | Ver4.02.00.D | Bug
| ARDAAAF-1966 | SPI | Incorrect clock reference is used to calculate the SPI baud rate | As per the requirement AR_PN0063_FR_0009, the parameter "SpiClockFrequencyRef" is referred to the MCU PLL clock to calculate the SPI baud rate. But the baud rate shall be calculated based on the CLKP_C clock, not with the PLL. CLKP_C is the actual clock used for SPI which is derived from PLL with the settings provided by the Mcu parameter McuPLLClk1DividerSel. In the current implementation, PLL value is directly taken to calculate baud rate for setting the SLR bit. Also, The available clock selection for the parameter "SpiInputClockSelect" is mentioned as PCLK to PCLK_DIVBY_64 in PDF. But as per hardware manual, the clock reference is CLKP_C. Please change the naming in parameter definition file and Tool code | 1. CLKP_C shall be taken for calculating SPI baudrate(either via McuPLLClk1DividerSel or with a seperate mcu reference which provides the CLKP_C) 2. Clock source naming shall be corrected in Definition file and in toll code for the parameter SpiInputClockSelect(CLKP_C .. CLKP_C_DIVBY_64) | 1. PLL is taken instead of CLKP_C for calculating baudrate(for setting SLR bit and the CG_INFO 002) 2. Incorrect clock source name for the parameter SpiInputClockSelect | Generator, PDF | Open |  | Ver4.02.00.D | Bug
| ARDAAAF-1939 | PORT | Missing Null pointer check | Null pointer check missing during pointer dereference Pointer 'LpChangeablePinDet' returned from call to function 'Port_SearchDirChangeablePin' may be NULL and will be dereferenced Eg: Port_SetPinDefaultDirection() Pointer 'LpModeChangeablePin' returned from call to function 'Port_SearchModeChangeablePin' may be NULL and will be dereferenced Eg: Port_SetPinDefaultMode() A null pointer check is necessary before dereferencing 'LpChangeablePinDet'/'LpModeChangeablePin' even if a DET check is available when DET is ON | Null pointer check shall be available while dereferencing pointer | Missing Null pointer check while dereferencing pointer | Code | Open |  | Ver4.01.00.001 | Bug
24045 | ARDAAAF-1694 | ETH | Please describe the processor name CPU1(PE1) to UM, Release Note, Readme to clarify the conditions of running Mcal. | Please describe the processor name CPU1(PE1) to UM, Release Note, Readme to clarify the conditions and environment of running Mcal. For Instance, <device number> will be changed to <device number>(CPU1(PE1)) in readme.txt, Release Note.txt, Component UM and so on. According to the user manual, the Main CPU is called "CPU1(PE1)". | NA | NA | Document | Acceptance | Ver4.02.00.D | E4.40, Ver4.01.00, Ver4.01.00.001 | Bug
| ARDAAAF-1627 | ETH | Wrong Elapsed time in Eth_GetTimeOutValue function | The time-out handling in Eth_GetTimeOutValue function is wrong if the initial value equals to the current value. The check for elapsed time shall be as follows: if(LusTimeOutCount_Curr > LusTimeOutCount_Init) shall be changed to if(LusTimeOutCount_Curr >= LusTimeOutCount_Init) | Elapsed time check shall be as if(LusTimeOutCount_Curr >= LusTimeOutCount_Init) | Elapsed time check is if(LusTimeOutCount_Curr > LusTimeOutCount_Init) | Code | Acceptance | Ver4.02.00.D | Ver4.01.00 | Bug
| ARDAAAF-574 | DIO | API functions for loop-back test | To check the correctness of an output, another pin shall be used in loop back. This is a safety mechanism. So this issue is not relevant for a QM release. | API functions for loop-back test are supported. | API functions for loop-back test are not supported. | Code, Generator, PDF, Test, Sample, Document, Requirements | Analysis | Ver4.02.01.D | Ver4.01.00 | Feature
| ARDAAAF-1245 | PORT | The PORT Driver module shall provide atomic access to all ports and port pins. | Enter and exit of critical section protection are not followed correctly. | All the PORT registers should be accessed within critical section protection by the usage of exclusive area | All the PORT registers are not accessed within critical section protection by the usage of exclusive area. | Code | Analysis |  | Ver4.02.00.D | Feature
| ARDAAAF-464 | ICU | Support for multiple configuration sets | The multiple configuration sets feature has many restrictions in the current ICU implementations which makes this feature almost unusable. 1. First major constraint: The customer complains that ICU cannot support different IcuChannelInputSelection (IcuGtmInputSelection is the corresponding P1x-C parameter) values between different configuration sets. 2. Second major constraint ICU does not support different number of channels (different values for IcuMaxChannel) between different configuration sets. As the ICU implementation is done from the scratch for P1x-C project and it is in a early development phase, we should focus to remove the limitations that we have on existing implementations. | ICU shall support different vaues for IcuChannelInputSelection and IcuMaxChannel parameters between different configuration sets. | ICU does not support different vaues for IcuChannelInputSelection and IcuMaxChannel parameters between different configuration sets. | Generator, PDF | Design | Ver4.02.01.D | E4.40, Ver4.00.00, Ver4.01.00 | Feature
| ARDAAAF-1801 | FLS | SYNCP instruction is missing before instruction-fetch after memory/register update | When the updated results of the control register or memory are to be used in the instruction fetch of the subsequent instruction, SYNCP instruction should be added before SYNCI for correct SW execution. So the the instruction sequence required shall be as follows: 1. Execute the store instruction to update a control register or memory (ST.W,etc.) 2. Perform a dummy read of the above control register or memory (LD.W etc.). 3. Execute SYNCP. 4. Execute SYNCI. 5. Execute the subsequent instruction (branch instruction, etc.). | When the updated results of the control register or memory are to be used in the instruction fetch of the subsequent instruction, SYNCP instruction should be added before SYNCI for correct SW execution. | When the updated results of the control register or memory are to be used in the instruction fetch of the subsequent instruction, SYNCP instruction is not executed before SYNCI. | Code | Open |  | Ver4.01.00.001 | Bug
| ARDAAAF-1872 | GPT | ISR not enabled when wakeup is enabled for corresponding channel | Precompile switch to enable Channel ISR is not always turned ON when wakeup is enabled for corresponding channel As a result notification to Ecum will be missed from Gpt_CbkNotification() Call sequence: Gpt_Init() -> Gpt_EnableWakeup() -> Gpt_StartTimer(); | ISR shall be enabled for the wake up enabled channel Documentation in UM shall be available for cases where ISR shall be enabled | ISR not enabled for the wake up enabled channel | Generator, Document | Open |  | Ver4.01.00.001 | Bug
| ARDAAAF-2001 | FLS | The implementation of Write-Verify FENTRYR register in Fls_FcuSwitchMode function is wrong. | In Fls_FcuSwitchMode() function, immedietly after the write operation to FENTRYR register, write/verify is executed to confirm FENTRYR write to switch FCU mode to programming/user mode was performed. But this check may get failed if write to FENTRYR is not completed before the read is done in the write/verify macro. | Register write verify of FENTRYR shall be done after the mode change is performed bacause the mode may not changed immediately on some devices | Register write verify of FENTRYR is done immedietly after write operation. | Code | Design | Ver4.02.01.D | Ver4.02.00.D | Bug
| ARDAAAF-1618 | ETH | Wrong buffer handling in the function Eth_ProvideTxBuffer/Eth_Transmit | The function Eth_Transmit destroys the first 14 bytes of the frame data coming from the upper layers, it writes the destination and source address + frame type on top of the already received data from EthIf. As per AUTOSAR R4.2 SWS_EthIf_00147, It looks that Tx and Rx Buffer refers to the payload of the Eth Frame and hence the skipping of first 14 bytes shall be avoided. | Buffer includes the payload only. | Buffer is assumed as the complete Ethernet Frame(Header + Payload) | Code | Design | Ver4.02.01.D | Ver4.01.00 | Bug
| ARDAAAF-1779 | ETH | Missing Ethernet Frames during transmission in Interrupt Mode | In the current Ethernet driver, some of the transmit frames are found to be missed in the following sequences when testing in Interrupt mode. 1. When Tx Confirmation enabled and interrupts are disabled and tried to send 40 packets, each are 64 byte in size, all 40 messages are not getting transmitted. 2. If Tx confirmation is disabled, only the first packet is sent and rest of the packets were not sent. No errors were observed as well. | No transmit frames shall be missed. | Some of the transmit frames are getting missed. | Code | Design | Ver4.02.01.D | Ver4.01.00, Ver4.01.00.001 | Bug
| ARDAAAF-1565 | ETH | Missing Ethernet Frames during transmission in POLLING mode | In the current Ethernet driver, some of the transmit frames are found to be missed in the following sequences. 1. When Tx Confirmation enabled and interrupts are disabled and tried to send 40 packets, each are 64 byte in size, all 40 messages are not getting transmitted. 2. If Tx confirmation is disabled, only the first packet is sent and rest of the packets were not sent. No errors were observed as well. | No transmit frames shall be missed. | Some of the transmit frames are getting missed. | Code | Design | Ver4.02.01.D | Ver4.01.00, Ver4.01.00.001 | Bug
| ARDAAAF-1112 | SPI | Code generator validations were missed when driver was ported from P1x | Many validations were added in P1x driver during the last releases. These validations were missed while the driver was ported to P1x-C. As a result, P1x-C code generator may fail to detect invalid configurations which may lead to unexpected behaviour of driver. | All code generator validations should have been ported when the driver was ported from P1x. | Many code generator validations present in P1x are not there in P1x-C. The tool test plan also need to be updated to include tests for these validations. | Generator | Design | Ver4.02.01.D | Ver4.01.00 | Bug
| ARDAAAF-1798 | ETH | Eth_59_ProvideTxBuffer returns BUFREQ_E_BUSY during frequent transmit request | If we reduce the delay between transmit requests, then the function Eth_59_ProvideTxBuffer will return BUFREQ_E_BUSY and hence further transmission will be stopped. It seems the global flag Eth_59_GblBufferLock is not properly updated. Please find attached test script to reproduce the issue. | Transmission shall not stop at higher transmit rates | Transmission is stopping at higher transmit rates without a notification | Code | Analysis |  | Ver4.01.00, Ver4.01.00.001 | Bug
26341 | ARDAAAF-1309 | General | About the reason that <IMPLEMENTED-ENTRY-REF> doesn't exist in <BSW-SCHEDULABLE-ENTITY> by BSWMDT file | According to AUTOSAR_TPS_BSWModuleDescriptionTemplate.pdf, 'BswSchedulableEntity' is a BSW module entity, which is designed for control by the BSW Scheduler. It implements a so-called "main" function". As attribute 'implementedEntry' is mandatory for 'BswModuleEntity', so <IMPLEMENTED-ENTRY-REF> should be presented in <BSW-SCHEDULABLE-ENTITY>. But in the current implementation, <IMPLEMENTED-ENTRY-REF> tag is not presented as a child of <BSW-SCHEDULABLE-ENTITY>. | <IMPLEMENTED-ENTRY-REF> tag should be presented in <BSW-SCHEDULABLE-ENTITY>. | <IMPLEMENTED-ENTRY-REF> tag is not presented in <BSW-SCHEDULABLE-ENTITY>. | PDF | Acceptance | Ver4.02.00.D | Ver4.01.00 | Bug
| ARDAAAF-2045 | SPI | SPI Driver does not Recover Normal Communication After Error Injection/Detection | The sequence tx has sent every 2ms on CSIH2. The sequence consists of 1 job / 1 ch so 2ms is more than enough time for the SPI tx to complete. Step1) Generate or inject the parity error.The SPI driver detects the parity error, and the error ISR handler SPI_CSIH2_TIRE_ISR is executed one time only. Step2) The SPI sequence status is correctly set to SPI_SEQ_FAILED. After this, subsequent calls to Spi_AsyncTransmit() results in SPI_SEQ_PENDING and seq tx never completes successfully even though the error condition has been removed | The SPI driver should report seq failure when the error condition is present but once the error condition is removed, seq transfer should resume normally | The SPI driver should report seq failure when the error condition is present but once the error condition is removed,subsequent calls to Spi_AsyncTransmit() results in SPI_SEQ_PENDING and seq tx never completes successfully even though the error condition has been removed | Code | Open |  | Ver4.01.00, Ver4.02.00.D | Bug
| ARDAAAF-2044 | SPI | The global variable 'Spi_Gaajobqueue' is getting updated with wrong jobindex values when interrupt occurs | The global variable 'Spi_Gaajobqueue' is getting updated with wrong jobindex values when interrupt (transmission or reception or any other interrupts)occurs .This is because the global variable 'Spi_Gaajobqueue' is not protected with critical section projection when jobs are pushed to the queue. This creates Job/Seq Pending state ,blocking the transmission. | All configured jobs should be pushed to 'Spi_Gaajobqueue' evenif an interrupt occurs | The global variable 'Spi_Gaajobqueue' is getting updated with wrong jobindex values when interrupt occurs | Code | Open |  | Ver4.02.00.D | Bug
| ARDAAAF-2043 | SPI | SPI Driver Incorrectly Reporting Job/Seq Pending when sequences are called in different tasks repeatedly for asynchronous transmission For single and Multiple HW Units | When sequences are called using Spi_Asynctransmit function from different tasks repeatedly,some of the sequences get failed after a long successful run. This issue is applicable for single and Multiple HW Units For Eg: Task1: Called in every 4 ms Time delay (2 sequences are called) Task2: Called in every 2 ms Time delay(3 sequences are called) Task3: Called in every 2 ms Time delay(6 sequences are called) Task4: Called in every 2 ms Time delay(6 sequences are called) Check status of sequences every time before the sequence is called inside tasks. | Sequences should be transmitted successfully | Sequences are not transmitted successfully | Code | Open |  | Ver4.01.00, Ver4.02.00.D | Bug
| ARDAAAF-1750 | WDG | <Msn>DemEventParameterRefs container multiplicity | As per Autosar SWS of WDG module, the WdgDemEventParameterRefs container and its parameters WDG_E_DISABLE_REJECTED and WDG_E_MODE_FAILED are non mandatory. if WdgDemEventParameterRefs container is not configured, compilation throws an error. | No compilation error expected when a non-mandatory container is not configured | Compilation expected when a non-mandatory container is not configured | Code, Generator, PDF | Analysis |  | Ver4.01.00.001 | Bug
| ARDAAAF-1997 | FLS | No sufficient tool validation available for FLS | Tool validation is not done for following scenarios. # If parameter FlsFdlCpuFrequency is not configured. # If FlsEccSedNotification and FlsEccDedNotification not followed C-syntax # To check values configured for parameters FlsEccDedNotification and FlsEccSedNotification are unique # To check values configured for parameters in FlsDemEventParameterRefs is same across multiple configuration set # To check value of parameter FlsMaxReadFastMode is greater than FlsMaxReadNormalMode # To check FlsTotalSize is equal to FlsNumberOfSectors * FlsSectorSize # To check value configured for the parameter FlsCallCycle is greater than '0' if the parameter FlsTimeoutMonitoring is set as TRUE # To check whether FLS_E_ECC_FAILED in the container FlsDemEventParameterRefs is configured when parameter FlsFaciEccCheck is configured as true. # To check whether the parameter FlsTimeOutCountValue in the container FlsConfigSet have a value when FlsTimeoutMonitoring is configured as true. | Tool validation should be present for all possible error scenarios. | Tool validations are not sufficient. | Generator | Open |  | Ver4.02.00.D | Bug
| ARDAAAF-2004 | WDG | DEM - WDG_E_REG_WRITE_VERIFY cannot be tested for WDTAnWDTE and WDTAEVAC | With the current implementation of the WDG MCAL, the WRITE_VERIFY DEM is supposed to be reported for the WDTAnWDTE and WDTAEVAC registers check_write_verify fails. But this problem with this implementation is that as soon as an error is injected (i.e as soon as the WDG detects an error) to these registers, a WDG reset occurs which means that the comparism phase of the code (i.e where the value of the register and the expected value is compared) and the DEM reported phase will never be reached. This means that if there is a failure for these registers, the current implementation of the MCAL will not allow for the DEM to be reported to the upper layer. Please note that the behaviour of the WDG from a hardware point of view is as documented in the respective F1x device manuals. | There should be a means of checking for the write verify DEMs for the WDTAnWDTE and WDTAEVAC registers or finding another method of error notification when there is an illegal write to these registers, with consideration given to hardware limitations | The error detection method implemented for illegal values being updated in the WDTAnWDTE and WDTAEVAC registers does not work. | Code | Open |  | Ver4.02.01.D | Bug
| ARDAAAF-1796 | General | Issues in MCAL code generator TOOL and Required Enhancement. | This ticket was created to track the existing bug in the MCAL code Gen tool, which is used as code generation tool in P1x-C projects. 1. The main issue however is that code generator does not returns -1 value when the option *stoponfirsterror* is set as *"false"* in the config.xml file of a particular module even if there are generation error detected, this however works fine if we use *stoponfirsterror* option as *"false"*. For eg: In ICU module the tag in the config xml looks like this currently: ¦<?xml version="1.0" encoding="UTF-8"?> <codegenerator {color:#d04437}stoponfirsterro{color}r="{color:#8eb021}false{color}" deleteoutputfileonerror="true">¦ The reason why this is preferred to be kept as false is: If suppose we have 5 errors in the configuration .arxml file and we keep the option stoponfirsterror as true then what happens is that the generator will report only the first error it encounters and will stop validating any further. So when we rectify the error then if there is any other error it will be reported after that. But if we keep this option as false then all the errors and warnings are listed in a single go, such that the user can rectify all the errors in the configuration in one go and need not re-run the Tool again and again. This seems to be a limitation in MCAL Code gen which restricts us to keep the option stoponfirsterror as true to get the return value as '-1' . 2. This is just a type of enhancement, as we can see is that for each template file the validate.vm is always included in the config.xml file ¦ <template> <templatefile>/../Template/Icu_Cfg_h.vm</templatefile> <outputfile>Icu_Cfg.h</outputfile> <includefile>/../../../../common_family/generator/CommonHelper.vm</includefile> {color:#d04437} <includefile>/../Validate/Icu_Validate.vm</includefile>{color} </template> ¦ but this makes some messages to be redundant as the validate file is rerun for all files. It would be much better if a particular message is generated only once. So that the generation window looks more good and easily readable. Also there can be some method to list the number of unique errors, warnings and information if any. A similar approach as the F1x tool code uses to display. | 1. Code generator should return -1 value when the option stoponfirsterror is set as "false". Basically it should be irrespective of any options and always throw a -1 value when generation error occurs. 2. There should not be any message that is redundant or repeated more than once instead all errors, warning and information messages should occur only once for any parameter or container. | 1. Code generator does not returns -1 value when the option stoponfirsterror is set as "false" . 2. Some Messages are redundant or repeated more than once. | Generator | Analysis |  | Ver4.00.00, Ver4.02.00.D | Bug
| ARDAAAF-417 | Fr | When data transfer is used, first FIFO frames are lost. | FIFO structure pointers are not configured inside FIFO pointer table during initialization. They are set only when API Fr_ReceiveQueue_Table() is invoked. In this case, the first FROTC.FTM FIFO frames will be lost, until FIFO table is configured with proper addresses. Same issue is valid also for the normal output pointer table, not only FIFO pointer table. The output pointer table also needs to be configured with data structure addresses during initialization. | FIFO structure pointers are configured inside FIFO pointer table during initialization. | FIFO structure pointers are configured inside FIFO pointer table only when API Fr_ReceiveQueue_Table() is invoked. | Code | Acceptance | Ver4.02.00.D | E4.40, Ver4.00.00, Ver4.01.00 | Bug
| ARDAAAF-378 | Fr | The data is not copied if frame is configured with Length less than or equal to 2 | In FR driver the data length to be calculated is not updated properly. In the current implementation when the frame is cofigured as 2 the data length value will be 1 and hence all the received data bytes are not copied. | The data should be copied correctly. | The data is not copied correctly | Code | Acceptance | Ver4.02.00.D | Ver4.00.00, Ver4.01.00 | Bug
| ARDAAAF-1246 | PORT | The Production error should not be switched OFF in the driver. | As per AUTOSAR requirement PORT139, The detection of production code errors cannot be switched off. But As per the MRS(EAAR-RS-0062) requirement(EAAR_PN0062_FR_0077), PortDemErrorDetect is should be added in the ' PortGeneral' to switches on/ off the Dem Error Detection and Notification. If this issue is considered as Safety impact, The requirement EAAR_PN0062_FR_0077 need to be removed from MRS(EAAR-RS-0062) If this DEM is switched off, error (if occurs) will not be notified to the user, which will leads to impact on safety. This ticket is a result from [safety analysis¦https://172.29.44.209/automotive/autosar/svnASG_D008633/dev/bsw/Autosar_R40/branch/dev_mcal_P1x-C_R403-OpenMarket/internal/X1X/P1x-C/modules/port/docs/safety_analysis/V4.02.00.D_P1x-C_R4.03_MCAL_Software_Safety_Analysis_PORT.xlsx], FMEA FMEA_PORT_005. | MRS Update is required. The requirement EAAR_PN0062_FR_0077 need to be removed from MRS(EAAR-RS-0062). | The requirement EAAR_PN0062_FR_0077 of MRS(EAAR-RS-0062) is stated to add the PortDemErrorDetect switch in ' PortGeneral' of PDF to switches on/ off the Dem Error Detection and Notification. | Document | Analysis |  | Ver4.02.00.D | Feature
| ARDAAAF-1820 | FLS | FLS timeout error is triggered incorrectly in case of out-of-sync call to Fls_MainFunction | It is assumed that user application should schedule Fls_MainFunction with the exact period time being specified in FlsCallCycle parameter. However, it cannot always be guaranteed the time span between call to Fls_Write() and (the first) call to Fls_MainFunction() is exactly matching the period time (FlsCallCycle), because they are called from different task threads. Based on the current timeout implementation, in case the time span from Flash job request (e.g. call to Fls_Write) to the first time call to Fls_MainFunction() is shorter than the time period specified in FlsCallCycle parameter, timeout error is triggered incorrectly. | In case out-of-sync (first time) call to Fls_MainFunction(), timeout error should not be triggered. | In case the time span from Flash job request to the first time call to Fls_MainFunction() is shorter than the time period specified in FlsCallCycle parameter, timeout error is triggered incorrectly. | Code | Design | Ver4.02.01.D | Ver4.01.00.001 | Bug
| ARDAAAF-1684 | SPI | ddDirectAccessQueueSize generated with wrong value | ddDirectAccessQueueSize indicates the lowest queue index for FIFO mode calculated after allocating space for direct access mode. But ddDirectAccessQueueSize is generated as zero for a configuration in which both direct access mode and FIFO mode are configured. This leads to a scenario where jobs for direct access mode get overlapped by jobs for FIFO mode inside the queue. | ddDirectAccessQueueSize should be generated with correct value | ddDirectAccessQueueSize generated with wrong value | Generator | Analysis |  | Ver4.01.00, Ver4.01.00.001 | Bug
| ARDAAAF-1831 | SPI | CG throws error when non-mandatory parameters are not configured | In the Adc description files, bool parameters are defined with multiplicity 0..1. During generation, error occurs when these parameters are not configured. Also the error messages are not proper Similar issues are present in other modules as well and shall be checked against parameters and containers | Validation check shall be done correctly and error messages shall be understandable | Validation check shall are not correct | Generator | Open |  | Ver4.01.00.001 | Bug